## Non-UI namespaces
Namespace | Status | Validation criteria
Ti.Accelerometer | To do. No Anvil tests. | to do
Ti.Analytics | To do. | to do
Ti.API | No Anvil tests. System log used everywhere and works. | See Status
Ti.App | Anvil pass | Anvil pass
Ti.App.Properties | Anvil pass | Anvil pass
Ti.Blob | Anvil pass | Anvil pass
Ti.BlobStream | Not implemented in MW. Will skip. | -
Ti.Buffer | skip | -
Ti.BufferStream | skip | -
Ti.Codec | skip | -
Ti.Contacts | Implemented by GL using Tizen Device API. Async functions are added in separate namespace. | Own Contacts sample app
Ti.Facebook | Kitchen sink was fixed to enable operation on Mobile Web. But Tizen implementation requires Tizen facebook client which is not available. | -
Ti.Filesystem | Anvil pass. Tests using Buffer and Stream were disabled. Implementation uses HTML5 and works with local storage only. | Anvil pass
Ti.Geolocation | Kitchen sink: fixed, works when GPS is enabled. Web-based geolocation doesn't work. Mail sent. | Kitchen sink OK
Ti.Gesture | To do. Implemented in MW, but not verified. No Anvil tests. | to do
Ti.IOStream | skip | -
Ti.Locale | To do. Incomplete MW implementation. | to do
Ti.Map | Kitchen sink was fixed to enable operation on Tizen. | Kitchen sink OK
Ti.Map.Annotation | To do. No Anvil tests. Probably works. | to do
Ti.Map.View | To do. No Anvil tests. Probably works. | to do
Ti.Media | CreateAudioPlayer implemented by GL. Two more functions implemented in Mobile Web. The rest of the namespace is not implemented. Work currently not planned. | Own test code
Ti.Media.AudioPlayer | Implemented in full using HTML5 by GL. | Own test code
Ti.Media.Sound | Implemented in full using HTML5 by GL. | Own test code
Ti.Media.VideoPlayer | Most important functionality is implemented using HTML5. | Kitchen sink OK
Ti.Network.HTTPClient | Anvil pass. Current HTML5 implementation is incomplete. | Anvil pass
Ti.Platform | Implemented by GL partially using Tizen Device API. Some functions cannot be implemented due to Tizen API limitations. | Anvil pass and own test code
Ti.Utils | Anvil pass. | Anvil pass
Ti.XML | Anvil fail; partially works, but has implementation issues
Ti.Yahoo | Anvil pass. | Anvil pass

## UI namespaces
Kitchen sink path |  |  |  |  | Status | What was done by GL | Notes
Base UI
| Tab Groups |  |  |  | (-; missed entry)
Window properties
|  | Change BG color |  |  | (+)
|  | Change BG image |  |  | (+)
|  | Toogle height/width |  |  | (+)
|  | Toogle opacity |  |  | (+)
|  | layout dimension properties |  |  | (+)
| Window layout |  |  |  | (can't save entered information; is this error?)
Window (standalone)
|  | open (plain) |  |  | (+)
|  | open (nav bar covered) |  |  | (+) | fixed partially (window opens, but no animation)
|  | tradditional modal |  |  | (-; missed on tizen)
|  | open (Fullscreen) |  |  | (+)
Views
|  | events propagations |  |  | (+)
|  | events interactions |  |  | (+)
image views:
|  |  | basic |  | (+)
|  |  | image file |  | (+) | fixed
|  |  | Remote image |  | (+)
|  |  | Image Scalling |  | (-; dimansions unavailable)
|  |  | Image View Positioning |  | (+) | fixed | checking status === 0 in index file
|  |  | Animated |  | (+) | fixed | Fixed for Tizen. You should decrease time interval on Emulator for correct animation. It works too slow for default values.
|  |  | Image View Encodding |  | (+) | fixed
|  |  | Image Rapid Update |  | (+)
|  |  | Android drawable resource |  | (-; missed on tizen)
scroll views
|  |  | Basic |  | (+)
|  |  | scrolling tabs |  | (+)
|  |  | -> scrolable view |  | (+)
|  |  | -> many on a screen |  | (+)
|  |  | -> scroll views textarea |  | (-)
table views
|  |  | -> Basic |  | (+)
|  |  | -> perfomance |  | (+)
|  |  | -> custom raw data |  | (+)
|  |  | -> headers |  | (-; undefined is not a function)
|  |  | -> footers |  | (+)
|  |  | -> table api Basic |  | (+)
|  |  | -> table custom row header |  | (+)
|  |  | -> table section header |  | (+)
|  |  | -> table empty dataset (create) |  | (+)
|  |  | -> append row |  | (+)
|  |  |  | append row with height | (-; TypeError: 'undefined' is not an object)
|  |  | -> delete row |  | (+)
|  |  | -> insert row |  | (+)
|  |  |  | insert row below -1 | (-; TypeError: 'undefined' is not a function)
|  |  | -> update row |  | (+)
|  |  | -> set row data |  | (-; undefined is not an object)
|  |  | -> row data from sections |  | (+)
|  |  | -> remove all rows |  | (+)
|  |  | -> empty table view |  | (+)
|  |  | -> table auto height |  | (+)
|  |  | -> refresh table view |  | (+)
|  |  | -> table view scroll indicators |  | (+)
|  |  | -> composize (partial size) |  | (+)
|  |  | -> table view (layout) |  | (+)
|  |  | -> table view (layout 2) |  | (+)
|  |  | -> table search |  | (-; missed)
web Views
|  |  | -> external url |  | (-; open bu empty page. error -> Message( 2223): Refused to display document because display forbidden by X-Frame-Options.)
|  |  | -> local url |  | (-; etc/local_webview.html (17) :ReferenceError: Can't find variable: Titanium; error -> etc/local_webview.html (17) :ReferenceError: Can't find variable: Titanium)
|  |  | -> XHR to FileSystem |  | (-; open google search page; error "Message( 2223): Refused to display document because display forbidden by X-Frame-Options." when try to do smth)
|  |  | -> Image URL |  | (+)
|  |  | -> Inline HTML |  | (+)
|  |  | -> Inline HTML w/ Trans Bg |  | (+)
|  |  | -> Inline HTML w/ Color Bg |  | (+)
|  |  | -> Basic Auth |  | (-; TypeError: 'undefined' is not a function)
|  |  | -> Logging and Unicode |  | (+)
alert dialog
|  |  | -> basic alert |  | (+)
|  |  | -> alert 2 buttons |  | (+)
|  |  | -> alert 3 buttons |  | (+)
|  |  | -> Double alert |  | (+)
|  |  | -> cancel alert |  | (+)
|  | options Dialog |  |  | (different options)
|  |  | -> show dialog 1 |  | (+)
|  |  | -> modify and show dialog |  | (+)
|  |  | -> show cancel button |  | (-; missing)
|  |  | -> modify and show Dialog |  | (-; missing, but "Show w/hide", instead)
|  | remove views |  |  | (+)
|  | zIndex |  |  | (+)
|  | Email dialog |  |  | (-; open but empty page; error -> TypeError: 'undefined' is not a function)
|  | Point Conversion |  |  | (+)
|  | View w/Size |  |  | (-; missed entry)
|  | Map view |  |  | (-; missed entry) | fixed | 1.Kitchen Sink\Resources\ui\common\baseui\map_view.js have put right check for platforms. if (!isAndroid && !isMW) { //code for Ipnone } else if(isAndroid) { //code for Android } 2.Kitchen Sink\Resources\ui\common\baseui\views.js Enable map view for mobileweb and Tizen //{title:'Map View', hasChild:!isMobileWeb, test:'ui/common/baseui/map_view', touchEnabled:!isMobileWeb, color:isMobileWeb?"#aaa":"#000"} {title:'Map View', hasChild:true, test:'ui/common/baseui/map_view', touchEnabled:true, color:"#aaa"}
| Custom events |  |  |  | (ok)
- Fire event 1
- Fire event 2
- Fire event 3
| Window Events |  |  |  | (ok)
| Vertival Layout |  |  |  | (ok)
Basic
Table View
| Horisontal Layout |  |  |  | (ok)
| Preferences |  |  |  | (-; missed) | not fixed | It is only Android option. It uses T.UI.Android namespace
| Hide Soft Keyboard (android) |  |  |  | (-; missed)
| Window soft input (android) |  |  |  | (-; missed)
| Menu (android) |  |  |  | (-; missed)
Controls
Slider
|  | -> Basic |  |  | (+)
|  | -> change min/max |  |  | (+)
|  | -> min/max range |  |  | (-; missed)
| Switch |  |  |  | (+)
| Activity indicatior |  |  |  | C
| Progress bar |  |  |  | (+)
| Button |  |  |  | (+)
Label
|  | Basic |  |  | (+)
|  |  | hide/show |  | (+)
|  |  | change label 2 |  | (+)
|  |  | label 1 background |  | (-; disabled -> I can't click)
|  | auto link |  |  | (-; missed) | not fixed | It is only Android option. It uses T.UI.Android namespace
Text fild
|  | Events |  |  | (+)
|  |  | focus |  | (+)
|  |  | blur |  | (+)
|  |  | hide/show |  | (+) | fixed | Changed top position of the label for tizen and mobileweb
|  | the Rest |  |  | (+)
|  | keyboard |  |  | (-; missed)
|  | border style |  |  | (-; missed)
|  | soft input focus |  |  | (-; missed)
Text area
|  | basic |  |  | (+)
|  |  | togge "editable" |  | (???; nothing happens -> is this an error?)
| Button states |  |  |  | (-; missed)
| Search bar |  |  |  | (-; missed)
| Picker |  |  |  | (-; missed)
Phone
Play movie
|  | local |  |  | (+)
|  | Phone |  |  | (+)
vibrate
|  | vibrate |  |  | (???; we can't check it without device)
| geolocation |  |  |  | (???, open but all data undefined and its dont work in android) | fixed partially | The first thing that titanium is disallowed from running reolocation services. Also Titanium.Geolocation.ACCURACY_BEST constant missed. The code for selection coordinates in function forwardGeocoder() has been corrected for tizen platform because coordinates are placed in inner object but selects from outer. Coorditates are placed with event injector: invalid date - timestamp is not returned from the request. the rest works fine. GPS off (without coordinates): Only forward geo works (after changes in forwardRecorder()). Other data are undefined because callback function of the location event doesn't invoked. Nothing changes after correcting Titanium.Geolocation.ACCURACY_BEST and distanceFilter. Callback functions of navigator.geolocation.watchPosition() doesn't invoked.
| accelerometer |  |  |  | (-; coordinates are missed)
| contacts |  |  |  | (-; missed)
| sound |  |  |  | (-; missed entry)
| photo gallery |  |  |  | (-; missed entry)
orientation
|  | set landscape left |  |  | (-)
|  | Phon |  |  | (?; can't check because "set landscape left" doesnt work)
|  | reset orientation |  |  | (?; we can't check it but it seems it works because log info has been printed -> titanium/Ti/API.js (33) :[INFO] resetting orientation modes)
|  | open a Window |  |  | (+)
| camera |  |  |  | (-; missed entry)
| notifications |  |  |  | (-; missed, but option "shake" exist)
Platform
HRK
|  | error callback |  |  | (-; can't reach host)
|  | binary data |  |  | (-; exist but disabled)
|  | XML data |  |  | (-; exist but disabled)
|  | XML properties |  |  | (-; exist but disabled)
|  | file download |  |  | (-; exist but disabled)
|  | utf-8 GET/POST |  |  | (-; exist but disabled)
|  | cookies |  |  | (-; exist but disabled)
|  | setTimeout |  |  | (+)
| 2. Network |  |  |  | (-: some info is undefined; no errors in console -> may be it miror error)
3. Commong JS
|  | - test 1 -> |  |  | (+; test passed)
|  | - test 2 -> |  |  | (+; test passed)
|  | - test 3 -> |  |  | (-; test failed)
| 5. logging |  |  |  | (+; see log for output)
| 6. Application data |  |  |  | (-; missed entry)
| 7. Application events |  |  |  | (-; missed entry)
| 8. properties api |  |  |  | (+; see log for output)
| 9. database |  |  |  | (-; missed entry)
| 10. platform data |  |  |  | (-; open but some fields are undefined, need checking)
| 11. Filesystem |  |  |  | (+; "see log for details")
| 12. JS Includes |  |  |  | (+)
| 13. Set Timeout (timer) |  |  |  | (+)
| 14. Set interval (timer) |  |  |  | (+)
| 15. XML RSS |  |  |  | (-; missed enter)
| 16. Utils |  |  |  | (+)
| 17. JSON |  |  |  | (+)
| 18. JS search |  |  |  | (+)
| 19. Clipboard |  |  |  | (+)
| 20. Sockets |  |  |  | (-; missed enter)
connecting socket
listening socket
server and client example
| 21. Android servises |  |  |  | (-; missed on android but "Passing data (windows)"exists and its work)
V. Mashups
| 1. Twitter |  |  |  | (-; missed enter)
| 2. Foursquare |  |  |  | (-; missed enter)
3. facebook
login/logout
-> force dialog => false
|  |  | -> "connect with facebook" on android but "login" on Tizen |  | (-; won't connect to facebook, doesn't show login page)
|  | query |  |  | (-; need login)
|  | properties |  |  | (-; need login)
|  | publish stream |  |  | (-; need login)
|  | photos |  |  | (-; need login)
5. YQL
|  | yql local search |  |  | (+)
| 6. SOAP |  |  |  | (-; missed enter)