## Non-UI namespaces
Namespace | Status | Validation criteria | Details
Ti.Accelerometer | Tizen issue prevents from completion. Defect opened. | -
Ti.Analytics | Sends and receives responses, but no server stats visible. GL sent request to Appcelerator. | Anvil, own test code
Ti.API | No Anvil tests. System log used everywhere and works. | See Status
Ti.App | Anvil pass | Anvil pass
Ti.Blob | Anvil pass. Base64 encoding fixes were provided to enable functionality in many other places. See also: https://jira.appcelerator.org/browse/TC-1557 | Anvil pass
Ti.BlobStream | skip | -
Ti.Buffer | skip | -
Ti.BufferStream | skip | -
Ti.Codec | skip | -
Ti.Contacts | Implemented by GL using Tizen Device API. Async functions are added in separate namespace. | Own Contacts sample app
Ti.Facebook | Kitchen sink was fixed to enable operation on Mobile Web. But Tizen implementation requires Tizen facebook client which is not available. See https://developer.tizen.org/forums/web-application-development/facebook-login-tizen | -
Ti.Filesystem | Anvil pass. Tests using Buffer and Stream (out of scope) were disabled. Implementation uses HTML5 and works with local storage. | Anvil pass
Ti.Geolocation | Kitchen sink: fixed, works when GPS is enabled. Web-based geolocation doesn't work; issue is related to Tizen (defect opened). | Kitchen sink OK
Ti.Gesture | Depends on Ti.Accelerometer, which doesn't work on Tizen. | -
Ti.IOStream | skip | -
Ti.Locale | Incomplete MW implementation. GL is adding functionality using JavaScript (new methods getCurrencyCode, getCurrencySymbol, getLocaleCurrencySymbol, Ti.String.formatCurrency); activity currently in progress. | Own test code
Ti.Map | Kitchen sink was fixed to enable operation on Tizen. | Kitchen sink OK
Ti.Media | Most important functionality is implemented using HTML5. | Own test code; Kitchen sink
Ti.Media.AudioPlayer | Implemented in full using HTML5. | Own test code; Kitchen sink
Ti.Media.Sound | Implemented in full using HTML5. | Own test code; Kitchen sink
Ti.Media.VideoPlayer | Most important functionality is implemented using HTML5. | Own test code; Kitchen sink
Ti.Network.HTTPClient | Anvil pass. GL implemented new methods. Everything works, except: clearCookies(host), validateSecureCertificate, tlsVersion, enableKeepAlive, cache. | Anvil pass and own test code
Ti.Platform | Implemented by GL partially using Tizen Device API. Some functions cannot be implemented due to Tizen API limitations (macaddress, netmask, architecture, availableMemory, processorCount). | Anvil pass and own test code
Ti.Utils | Anvil pass. | Anvil pass
Ti.XML | Anvil tests are not valid. The core namespace functionality appears to work.
Ti.Yahoo | Anvil pass. | Anvil pass

## UI namespaces
Lists Kitchen sink issues that were handled by GlobalLogic, i.e. places in Kitchen Sink that did not work, compared to Kitchen Sink on Android. Places that worked "out of the box" are not listed.
Kitchen sink path | Status | Notes
Base UI -> Hide Soft keyboard (Android) | Fixed | Ti.UI.Tizen.hideSoftKeyboard() added
Base UI -> preferences | Not fixed | Titanium.UI.Android.openPreferences: Android only. No Tizen equivalent.
Base UI -> Tab Groups is missing | Fixed | In mobile web for BaseUI was missing property tabGroup. I added this property into the ApplicationTabGroup module.
Base UI -> Views -> Android drawable resources | Not fixed | Android specific.
Base UI -> views -> email dialog | Fixed | Tizen doesn't seem to support attachments, even without Titanium. Attachment adding was disabled in the test code.
Base UI -> Views -> Image views -> Animated | Fixed
Base UI -> Views -> Image views -> Image file | Fixed
Base UI -> views -> image views -> image scaling | Fixed
Base UI -> views -> image views -> image scaling | Fixed | Blob had to be modified (base64 support added)
Base UI -> Views -> Image views -> Image view position | Fixed
Base UI -> views -> image views -> remote image | Fixed | Add property to ImageView to descript default image.
Base UI -> views -> Map view | Fixed | Buttons +/- in Tizen (map zoom in-out) don't work. Plugin/Browser issue.
Base UI -> Views -> Options dialog | Fixed | The look and behavior of the Switch had to be modified: it now supports labels.
Base UI -> views -> options dialog -> modify and show Dialog | Fixed | Implemented by GL as Ti.UI.OptionDialog.tizenView
Base UI -> views -> options dialog -> show cancel button | Fixed
Base UI -> views -> Table views -> append row with height | Fixed | Animation during insertion not supported. revealed TableView bug (see https://jira.appcelerator.org/browse/TC-1580). Added added getIndexByName method to TableView.
Base UI -> views -> Table views -> Headers | Fixed | TableView was modified to support search bar and section headers
Base UI -> views -> Table views -> insert row below | Fixed
Base UI -> views -> Table views -> Set row data | Fixed
Base UI -> views -> view w/size | Not fixed | See https://jira.appcelerator.org/browse/TIMOB-10427
Base UI -> views -> web views -> external url | Fixed | Works for URLs that do not send X-Frame-Options: SAMEORIGIN. Google is sending an "X-Frame-Options: SAMEORIGIN" response header. This option prevents the browser from displaying iFrames that are not hosted on the same domain as the parent page.
Base UI -> views -> web views -> local url | Fixed
Base UI -> views -> web views-> Basic auth | Not fixed | Tizen's browser doesn't seem to handle HTTP authentication (ignores auth header). Tizen defect opened.
Base UI -> views -> web views-> XHR to FileSystem | Fixed
Base UI -> Window (standalone) -> open (Fullscreen) | Fixed | Notification area is not covered. Function webkitRequestFullScreen has no effect, although success callback is entered. This appears to be by design.
Base UI -> Window (standalone) -> open (nav bar covered) is missing | Fixed | Animating from center out, not from bottom right right (must tweak 2d matrix)
Base UI -> Window (standalone) -> tradditional modal is missing | Fixed | Method setLeftNavButton() doesn't work in MW; needed to add the button 'back' manually.
Base UI -> Window soft input (android) | Not fixed | Android only. No Tizen equivalent.
Controls -> Label -> AutoLink | Fixed | AutoLink property added to Label.
Controls -> Label -> Basic -> Label 1 Background | Fixed
Controls -> Picker | Fixed
Controls -> Search bar | Fixed | Ti.UI.SearchBar implemented.
Controls -> Slider -> Min/Max range | Fixed | Implemented in HTML5
Controls -> Switch | Fixed
Controls -> Text field -> Border style | Fixed
Controls -> Text field -> Events -> Hide/show | Fixed
Controls -> Text field -> Keyboard | Fixed partially | Only 4 types of keyboard are supported by HTML5 - more than keyboard types in Titanium. Those are not working in Kitchen Sink.
Controls -> Text field -> Soft input focus | Fixed | added Ti.UI.Tizen.hideKeyboard() and a couple of constants
Controls -> TextArea -> Basic -> Toggle editable | Fixed | Added property for disabling textarea in TextBox (editable). Fix toogle button (update _capitalize function in TextBox).
Mashups -> Facebook | Not fixed | See Ti.Facebook in the first sheet
Mashups -> Foursquare | Not fixed | Foursquare requires registration of the client application, like Facebook. There is no options for Tizen in the registration, and Mobile Web apps require server callbacks. The old API used in Kitchen Sink is now inactive.
Mashups->Twitter | Fixed
Phone -> Accelerometer | Not fixed | See Ti.Accelerometer in the first sheet
Phone -> Camera | Not fixed | Shows momentarily, but closes immediately. See https://bugs.tizen.org/jira/browse/TIVI-254
Phone -> Geolocation | Fixed partially | Works when the GPS is on (via event injector). Works partially when the GPS is off. See Ti.Geolocation in the first sheet.
Phone -> Notifications | Fixed | Notifications are implemented using HTML5.
Phone -> Notifications -> Shake | Not fixed | Depends on accelerometer
Phone -> Orientation | Not fixed | Depends on accelerometer
Phone -> Photo gallery | Fixed
Phone -> Screenshot | Fixed | Implemented in HTML5
Phone -> Sound | Fixed partially | There are Kitchen Sink tests that assign a file object to Ti.Sound's URL string property, and therefore fail. They were deactivated. There are KS tests where remote URL is used with Ti.Sound (instead of Ti.AudioPlayer as per doc). Reset button doesn't work correctly there.
Platform -> Application data | Fixed
Platform -> Application events | Not fixed | Such application events are not supported on Tizen. Only Android 4 platform implements them.
Platform -> CommonJs -> test3 | Fixed
Platform -> Database | Not fixed | No Tizen equivalent; webSQL is asynchronous.
Platform -> Locale | Fixed
Platform -> Network | Not fixed | Requires navigator.connection, which is undefined.
Platform -> Platform data | Fixed partially | Whatever unsupported on Tizen is missing
Platform -> Sockets | Not fixed | No Tizen equivalent
Platform -> XHR | Fixed